## Slide 1
Bental | Engineering Build Plan
YYYY | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  | 
MM | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
Paju |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C6.0 Build (3/29~7/21)
C6.1 Build (7/20~11/08)
C5.0 Build ( 11/08~ )
C4.0 Build (3/15~ )
C3.0 Build ( 8/01~ )
C2.0 Build ( 10/15~ )
MP
 | JUL |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV | 
FOL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EOL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tx, Compl OQC Tester |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SMT : 7/26~8/19(Mask Down selection DOE
Dot/Flood AlN attach : 8/04~8/24
Dot/Flood VCSEL attach : 8/05~8/29
Wire bonding : 8/11~12 LBU, 8/18~8/30 Main
FOL Test : 9/06~9/30
STM Main EOL/Comp/OQC
Housing Plasma : 7/18~7/20
OSA with STM : 7/22~~8/19
Active Align with STM main OSA: 8/10~10/13
STM Main config EOL Process
9/16~10/21
TSMC Main config EOL Process : 10/24~11/10
AA with TSMC OSA and DOE: 10/14 ~ 10/28
EOL process
LBU : 8/18~8/31
OSA With TSMC 8/20~8/28
Build Strat
: 7/13 7/18
Substrate ETA updated
Build End
: 11/13
1. Build Schedule
2. C6.1 Build plan : Ongoing
C5.0 Build ( 01/20~ ), New ASIC(Gila) (1/26~)
TSMV Main & DOE EOL/Comp/OQC
11/05~11/13
SW validation
EOL
CompliancOQC
LBU 8/31~9/05
As of this week

## Slide 2
Sphinx | Build status
Program | 22Y |  |  |  |  |  |  |  | 23Y |  |  |  |  |  |  |  | 
 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Sphinx-E/J |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sphinx- P/F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Build Status
- Sphinx-E/J C4.0 build is ongoing.
 LBU lot is in progress, and the first config is in FOL process
- Sphinx-P/F C4.0 will start in Nov.
 OK2build will be submitted in 10/25
10/17
C5.0
7/1
C5.0
7/29
C4.0
9/28
C4.0
11/2
C3.0
1/13
C3.1
3/10
C3.1
4/7
C2.0
4/21
AVB
11/7
Sphinx- J
OVB
2/13
Sphinx-E
OVB
3/20
Sphinx-P
PRB
4/10
PRB
5/18
PVT
6/6
PVT
6/19
C3.0
2/17
C2.0
5/19
AVB
12/12
Sphinx- F
Sphinx-E
Sphinx-F
Sphinx-P
Sphinx-J

## Slide 3
VR-P |  |  |  |  | Oct |  |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  | 
Build | Eng | Eng | C5.0 | 7/29 ~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C4.0 | 10/14~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C3.0 | 1/7~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C3.1 | 2/25~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C2.0 | 4/14~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Ops | Ops | AV1 | 10/24~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | AV2 | 11/11~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | OVB | 1/10~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | PRB | 4/1~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reliability |  |  | C5.0_Last | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C4.0 | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C3.0 | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Factory Readiness |  |  |  | Campus 4 (FOL) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C3.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Campus 4 (EOL) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C3.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Campus3 (TEST) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Item | ACE DRI | Due
Critical Decision point | - C3.0 design needs to be locked down after checking some of critical C5 REL items’ result. - Brahe(prism ass’y level) IPQC machine should be stable. Sometimes log can be disappeared. Barcode reading jig is not stable. YTC’s help is needed. - EE testers for pismo ass’y need to be optimized. E8M(for DCR), E3V(for TDR) UPH should be increased, and Pistoia(for LDR power) should be ready on time. - Jahwa config is not assigned during C4 build matrix. It means there is no chance to decide Jahwa VCM as MP POR. - C4 build plan is very tight since prism design locked down lately. | Cathleen, Eric, Ali YTC Jason, Alex, Pino Cathleen, Eric Cathleen, Eric | ‘23.11.30 ’22.11.19(C4 IPQC) ‘23.1.6(C3.0) ‘22.11.30(mid of C4.0) -
Master Plan
05

## Slide 4
WV |  |  |  | Oct |  |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  | 
Build | Eng | C4.0 | 9/19~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C3.0 | 12/18~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C3.1 | 2/12~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C2.0 | 3/26~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Ops | AVB | No plan@GM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | OVB | No plan@GM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Post PRB | 3/4~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | PPVT | TBD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reliability |  | C4.0 | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C3.0 | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Factory Readiness |  |  | Campus 4 (FOL) |  |  |  |  |  |  |  |  |  |  |  | C3.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Campus 4 (EOL) |  |  |  |  |  |  |  |  |  |  |  | C3.0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Campus3 (TEST) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
POR Blockers |  |  | Process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Material |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Item | ACE DRI | Due
Critical Decision point | None |  | 
WV | Master Plan
Notes: Main : 1인치, Ball type Sensor shift 적용가능성 (FPDC 최소화)
-Tele
1) 고배율 전개 가능성 & 시점 2) 지금 인물모드를 2,3배에서 잘쓰고 있는데 나중에 5배를 하게 되면 인물모드는 어떻게 하는지?
3) 텔레 카메라의 성능 강화 방향은 화질(센서 증가….) or 사용 배율 증가 어느 쪽이 맞다고 생각하는지?
S-wide
; 고화소 센서 적용 가능성 & 시점 1) Main sensor 화소가 48mp로 올라가는데 그에 맞춰 sub CM 화소도 같이 올라가는지 가능성 2) Sensor shift 를 wide 적용 가능성 /목적

## Slide 5
 | Item | ACE DRI | Due
Critical Decision point | OIS design: corner cut design Sensor quality and performance improvement VCM quality and performance improvement IQC tester: OIS/AF tester, MTF inf tester not yet available | Jordan Nandita YK/Erwin | C3.0
MW |  |  |  | Jun |  |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  | 
Build | Eng | C5.0 | 6/18~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C4.0 | 9/25~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C3.0 | 1/5~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C3.1 | 3/20~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C2.0 | 4/20~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | OVB | 1/22~ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | PRB | TBD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | PPVT | TBD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reliability |  | C4.0 | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | C3.0 | Drop test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | HTHH (250hrs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Factory Readiness |  |  | Campus 1 (FOL) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Campus 1 (EOL) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Campus3 (Test) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
POR Blockers |  |  | Process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Material |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MW LGIT | Master Plan
Notes: Item
ACE DRI
Due
Critical
Decision point
None.

## Slide 6
Project | 22Y |  |  |  |  |  |  |  | 23Y |  |  |  |  |  |  |  | 
 | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Peridot-J |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Peridot- P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Peridot-L/R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Peridot | Build status and plans
Peridot-J C4.0 build on-going
→ CALS, Compliance and CALRS bring up on-going / C4000F config FATP shipment : 11/7
Peridot-P C4.0 will be started from 10/31.
→ OK2build will be submitted in 10/25.
Paju(C6/C5/C4)
Gumi(C3/C2/PVT)
C5.0 5/21 ~
C4.0 9/26 ~
C3.0 1/4 ~
C3.1 3/1 ~
C2.0 4/12 ~
C5.0 7/13 ~
C4.0 10/31 ~
C3.0 2/8 ~
C3.1 3/29 ~
C2.0 5/12 ~
OVB 2/6 ~
PRB 3/20 ~
PRB 4/5 ~
OVB 3/6 ~
PVT 6/B ~
PVT 6/B ~
AVB 11/23 -
C5.0 6/M ~
10/28
Machine transfer
Paju → Gumi
12/16~
12/28~
1/15~

## Slide 7
Falcon | Falcon Organization
LGIT organized dedicated Falcon-Task group including automotive experienced members.
[Falcon Organization]
[History]
~’21.07
Reviewed RFQ
Event
Remark
~’21.12
Highlight from ACE
Request from ACE to increase members
who have automotive experience.
Falcon Members |  | Total
ACE | Automotive | 
8 | 5 | 13
Members |  | Total
ACE | Automotive | 
19 | 7 + (5) | 26
Organize technical support group: 5 eng’rs
~’22.01
1st strengthened roster
Current
Continuously Strengthen roster
Members |  | Total
ACE | Automotive | 
27 | 9 + (5) | 36
Organize technical support group: 5 eng’rs
Future
Reviewing Flexible M/M
Notes: Next plan이 있다면 team roster를 flexible adjust하는데 도움이 될 것이다.

## Slide 8
Project | Config | 22Y |  |  |  |  |  |  |  |  |  | 23Y
 |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
Otter | Mini/Set-up |  |  |  |  |  |  |  |  |  |  | 
 | Alpha |  |  |  |  |  |  |  |  |  |  | 
 | Small |  |  |  |  |  |  |  |  |  |  | 
 | Main |  |  |  |  |  |  |  |  |  |  | 
Eagle | Mini/Set-up |  |  |  |  |  |  |  |  |  |  | 
 | Alpha |  |  |  |  |  |  |  |  |  |  | 
 | Small |  |  |  |  |  |  |  |  |  |  | 
 | Main |  |  |  |  |  |  |  |  |  |  | 
Falcon | Mini/Set-up |  |  |  |  |  |  |  |  |  |  | 
 | Alpha |  |  |  |  |  |  |  |  |  |  | 
 | Small |  |  |  |  |  |  |  |  |  |  | 
 | Main |  |  |  |  |  |  |  |  |  |  | 
Falcon | C6.0 Build Status
Build Status
- Main build start: 11/07/2022
- Build sequence: Otter → Eagle → Falcon
→ New FPCB is used in main config.
→ Sony IMX728 ES3 sensor will be used from main config.
→ Cover case and window attach process will be skipped.
10/27
1/18
3/10
4/19
4/11
6/20
5/2
6/21
5/4
7/9
5/21
7/22
5/24
8/1
7/28
10/14
7/28
10/12
7/28
10/31
11/7
12/6
11/24
12/22
12/13
Input: 1.4K
Input: 0.6K
Input: 1.4K
Notes: Total C6.0 build schedule